## Sheet1
Work Packages | Estimations | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Work Hours
Download and install rude config | 0.5 | 2 | [15 empty] | 2
use rude config to parse | 1 | 1.4 | [15 empty] | 1.4
place config options into map | 1 | 0.2 | [15 empty] | 0.2
run as program | 0.2 | 0.3 | [15 empty] | 0.3
run as daemon | 0.2 | 0.3 | [15 empty] | 0.3
create .pid file | 1 | 2 |  | 1 | [13 empty] | 3
use config file | 1 |  |  | 1 | [13 empty] | 1
create log file | 0.2 |  |  | 1 | [13 empty] | 1
respond to a signal | 1 |  |  | 2 | [13 empty] | 2
inotify interface | 2 | [16 empty] | 0
versions folder | 1 | [16 empty] | 0
date stamps | 0.2 | [16 empty] | 0
copy files to versions folder | 0.2 | [16 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
Work Hours |  | 6.2 | 0 | 5 | 0
Remaining Effort | 9.5 | 3.3 | 3.3 | -1.7 | -1.7
Ideal Burndown | 9.5 | 7.125 | 4.75 | 2.375 | 0